| GOAL 1 – Action Plan Development- |
| --- |
| Goal | Develop a culture of collaborative inquiry throughout the city. |
| ACTION STEPS – | IMPLEMENTATION PLAN – |
| Section B – Descriptively list the action you plan to take to ensure you will be able to progress toward your goal. Action steps are strategies and interventions which should be scientifically based where possible and include professional development, technology, communication, and parent and community involvement initiatives within the action steps of each goal. | Section C – For each of the Action Steps you list, give timeline, person(s) responsible, projected cost(s)/required resources, funding sources, evaluation strategy and performance results/outcomes. (For Evaluation Strategy, define how you will evaluate the action step.) |
|  | Timeline | Person(s) Responsible | Evaluation Strategy | Performance Results / Outcomes |
| Action Step 1.1 | Hire the Business Intelligence Coordinator. | July 2012 | Laura Hansen | Employee Evaluation |  |
| Action Step 1.2 | Research best practices in data-informed decision making. | Ongoing | Margie Johnson | Documentation | Initial Research completed Aug. 2012 Research--ongoing |
| Action Step 1.3 | Develop guiding documentation to facilitate the implementation of a culture of collaborative inquiry. | Ongoing | Margie Johnson | Completion of guiding documents. | Draft Proposal—August 2012 Future Recommendation---To Be Completed June 3, 2013 |
| Action Step 1.4 | Collaborate with the Communications department to develop a communication and marketing plan for this initiative. | Ongoing | Margie Johnson | Completion of communication plan | Meetings began in November 2012. Data Warehouse Intranet---February 2013 (1310 views to date) Recommendation Plan---June 2013 (Monday Memo Article, Beginning School Year Kickoff, Monthly Newsletter) |
| Action Step 1.5 | Collaborate with various stakeholders to develop their collaborative inquiry professional learning plan. | Ongoing | Margie Johnson | Completion of plans Evaluation Frameworks developed by each stakeholder group. | L & L PL Committee REL & other grant opportunities Principal Book Study—April 2013; June 2013 Summer PD—Balanced Literacy; New Teacher Orientation; Technology Lora Hall—new teachers & university |
| Action Step 1.6 | Participate in continuous professional learning opportunities around data-informed decision making. | Ongoing | Margie Johnson | Documentation | Learning Forward 2012 various webinars & books |

| GOAL 2 – Action Plan Development- |
| --- |
| Goal | Develop sustainable and scalable, differentiated professional learning opportunities for stakeholders so that their capacity to make data-informed decisions is maximized. |
| ACTION STEPS – Template 4.2 | IMPLEMENTATION PLAN – |
| Section B – Descriptively list the action you plan to take to ensure you will be able to progress toward your goal. Action steps are strategies and interventions which should be scientifically based where possible and include professional development, technology, communication, and parent and community involvement initiatives within the action steps of each goal. | Section C – For each of the Action Steps you list, give timeline, person(s) responsible, projected cost(s)/required resources, funding sources, evaluation strategy and performance results/outcomes. (For Evaluation Strategy, define how you will evaluate the action step.) |
|  | Timeline | Person(s) Responsible | Evaluation Strategy | Performance Results / Outcomes |
| Action Step 1.1 | Hire the Business Intelligence Coordinator. | July 2012 | Laura Hansen | Employee Evaluation |  |
| Action Step 1.2 | Research best practices in data-informed decision making. | Ongoing | Margie Johnson | Documentation | Initial Research completed Aug. 2012 Research--ongoing |
| Action Step 1.3 | Conduct focus group meetings to develop common language and framework around data-informed decision making. | Ongoing | Margie Johnson |  | TBD---working on this one Through L & L PL Committee, did survey departments to see how they use data. |
| Action Step 1.4 | Develop a variety of professional learning resources for supporting data-informed decision making, including how-to videos, Quick Reference Guides, best practice videos, scenario-based e-learning modules, etc. | Ongoing | Margie Johnson | Documentation Library of Resources | Interviewed high user teachers to develop Recommendation—June 2013 Working with Kelly McKinney to get schoolnet access. TBD---working on this one Meeting with Laurie Smith to document. Working with Richard Frank. Spencer Foundation Grant |
| Action Step 1.5 | Collaborate with other departments to have data-informed decision making embedded into their professional learning opportunities. | Ongoing | Margie Johnson | Meeting Minutes Professional Learning Documentation | Summer PD—Balanced Literacy; New Teacher Orientation; Technology Lora Hall—new teachers & university L & L PL Committee |
| Action Step 1.6 | Establish partnerships throughout the community and nationally to support the implementation of a data-informed decision making professional learning plan. | Ongoing | Margie Johnson |  | REL, SCORE, Jenny Rankin (OCTD), EdSurge, ARCC, Learning Forward, NAZA |
| Action Step 1.7 | Develop a Data-Informed Decision Making Knowledge Management System. | July 2013 | Margie Johnson | System in Place | Working with Kelly McKinney Using Edmodo for Book Study. |